## Activity
Project Info |  |  |  |  | Targets |  |  |  |  | Report Q1 |  |  | Report Q2 |  |  | Report Q3 |  |  | Report Q4 |  |  | Annual Report
SN | Project name | Output | Indicator Name | Baseline | Target Q1 | Target Q2 | Target Q3 | Target Q4 | Annual target | Achievements | Performance | Comments | Achievements | Performance | comments | Achievements | Performance | comments | Achievements | Performance | comments | Achievements | Performance | comments
1 | Construction of the Centre for Biomedical Engineering and e-Health (CEBE) complex | 80 in-service professionals trained through short -courses | Number of in-service professionals trained through short -courses | 200 | 20 | 20 | 20 | 20 | 80 | 0 | 0% | The pool of trainers (consultants) is established and approved by the funder (AfDB). 3 short courses in biomedical engieering and e-health are advertized to be conducted in Q2. | 91 | 227.5% | 91 (23% female): 4 short-courses were organized including 1 in biomedical engineering and 3 in E-health.  Healthcare Technology Management (Number of trainees: 18 Male: 14 and Female: 4)  Medical coding (Number of trainees: 33 Male: 22 and Female: 11)  Security, Privacy and Legal Framework of Health Information Systems (Number of trainees: 18. Male: 16 and Female: 2)  Telemedicine Applications (Number of trainees: 22 Male: 16 and Female: 6
|  | 30 MSC students enrolled and trained | Number of Msc students enrolled | 0 |  | 30 MSC students enrolled |  |  | 30 MSC students enrolled | 0 | 0 | The developed curriculum of MSC in biomedical engineering has been reviewed and objected by the HEC. Indeed, there are a number of recommendations made by HEC to be addressed before accrediting the program including the establishment of laboratores and involvement of external highly qualified in the curriculum development process. These recommendations are being addressed and expected to resubmit the program to HEC by Q2. The existing MSc program in health informatics is being updated at College level to catter for E-health issues. | 0 | 0 | The curriculum of MSC in Bomedical engineering and MSc in E-health (Health informatics) are not yet accredited. Recommendations given by HEC have been addressed and the curricculum resubmitted to HEC for reasssessment. The Bachelor program in rehabilitation and mobility science is still under development. The supply of lab equipment is not yet done because the supplier provided a non-confirm bank guarantee which delayed the signature of contract. Currently, negotiations with the supplier are ongoing to comply with regulations. | To be updated
|  | CEBE complex constructed | % completion of construction works | 0 | 10% | 20% | 35% | 55% | 55% | 0% | 0% | The contract for the contractor has been concluded at UR level and submitted to MINIJUST for approval thereafter will be submitted to the Bank for approval. | 2% | 10% | Site installation and excavation, supply of initial construction material;
2 | UR Infrastructure Development | % completion of construction works | Percent | 12% | 40% | 55% | 65% | 75% | 75% | 15% | 15% | All the four sites (Huye, Nyagatare, Busogo, Nyarugenge) started and works are on track according to the newly agreed schedule. However, the low performance vis-à-vis the target is due to the observed delays in start up of construction works. Other components linked to the project are ontrack too: Long-term training whereby 15 UR staff have been sent to Korea for MSc program, and a team of Koreans is working on information management system to accompany the project. | 30.5% | 55.45% | HQ: 28.26% concrete works at 5th floor (on schedule); MG: 35.68% concrete works at roof slab (2nd floor building) (on schedule); ODL Nyagatare: 28.75% Concrete works at roof slab (G+1 building) (ahead of 3months of the schedule); ODL HUYE: 27.67% concrete works at roof slab (G+1 building) (ahead of 2 months compared to the schedule); ODL BUSOGO:2.7% Foundation (footings) with 15.86% of supplied materials (behind the schedule of 2 months);
3 | Regional Center Of Excellence For Vaccines, Immunization and Health Supply Chain Management (RCE-HSCM) | Research promoted in EAC countries | Number of Grant for evidence based research | 0 | 3 | 0 | 3 | 0 | 6 | 0 | 0 | A first meeting with the identified 30 regional researchers was held in Rwanda to establish the research agenda. Priorities towards a call for application scheduled in December 2019 have been set. | 0 | 0 | By December 2019, the database currently contains 337 documents on HSCM, up from 302 in July 2019.
|  | Training programs in VIHSCM established | In-service staff trained trough short-courses | 460 | 20 | 20 | 20 | 20 | 80 | 24 |  | 24 pharmacists from Rwandan Districts and hospitals have been trained in immunization supply chain management | 62 | 155% | 2 Short Courses were organized as follow: 1)Humanitarian Health Supply Chain: 31 participants 2)Immunization Supply Chain Management: 31 Participants mainly hospitals pharmacists and immunisation supervisors
|  |  | New students enrolled in MSc program | 29 | 30 | 0 | 30 | 0 | 60 | 40 |  | 40 new candidates including 18 Rwandan and 22 from the region since June 2019, for 2nd intake are enrolled and courses are being delivery as pe approved program | 40 | 133.3% | 1st cohort: 25 students graduated from Master of Health Supply Chain Management while 4 others are to finalize their thesis;2nd cohort: The first Semester (face to face and online) with field placement and exams were successfully concluded. Courses for the second semester started on December 2 with two weeks face to face.
|  | Regional Centre of Excellence for Vaccines, Immunization and Health Supply Chain Management (RCE-VIHSCM) constructed. | % completion of construction works | 0 | 5 | 15 | 25 | 30 | 30 | 0 | 0% | The evaluation report for prequalification of consultant to design the RCE building has been submitted to the Bank for approval thereafter the request for proposals will follow. | 0 | 0% | Upon approval of the evaluation report for prequalification of consultant to design the RCE building, a call for proposals from pre-qualified consulting firms is issued and opening is scheduled on 28/1/2020.
|  |  | equipment of RCE-VIHSCM building |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The equipment will be procured upon completion of the building | 0 | 0 | The equipment will be procured upon completion of the building
4 | Africa Center of Excellence for Innovative Teaching and Learning Mathematics and Science (ACE ITLMS) | 4 Research grants in Science Education awarded. | Number of Research grants awarded | 0 | 4 |  |  |  | 4 | 4 | 50% | The 4 grants have been awarded to the center's researchers as a result of evaluation of received proposals. Meanwhile, 3 new Research papers were published in peer reviewed journals and 2 staff have been facilitated to present their researches in international conferences. | 4 | 100% | In addition to the ongoing 4 researches supported by the center’s grants, 6 new scientific papers have been published in peer reviewed journals.
|  | 8 new PhD students and 23 Med enrolled in ACE-ITLMS | Number of new PhD and Msc students enrolled | 28 PhD students and 33 Msc students enrolled. |  | 8 new PhD students and 23 Med enrolled |  |  | 8 new PhD students and 23 Med enrolled | 0 | 50% | 10 new PhD and 45 new MSc applicants have been admitted to enroll in Q2. | New 10 PhD students and 68 Msc students enrolled including 21 international students. | 230% | During the Q2, the center has enrolled a total of 78 postgraduate students including 22 females. In addition to 45 candidates initially admitted in MEd, the center has opened a new teaching center at Remera Campus for private students whereby 23 students have been enrolled.
5 | African Center of Excellence in Data Sciences (ACE DS) | New PhD students and Msc enrolled in ACE-DS | Number of new PhD and Msc students enrolled | 44 PhD students and 54 Msc students |  | 3 new PhD students and 30 Msc students enrolled |  |  | 3 new PhD students and 30 Msc students enrolled | 0 | 50% | 43 new MSc applicants have been admitted to enroll in Q2. | 0PhD and 23 Msc students including 8 internationaL | 70% | Out of 43 admitted students, only 23 (12 female) have been able to enrol because their expectations were not met: the evening program suspended due to the insufficiency of faculty to cover it. Thus, most of Rwandan who would wish to enrol for evening mode while keeping their jobs turned off the obtained admission.
6 | African center of excellence in energy for sustainable development (ACE ESD) | New PhD students and Msc enrolled in ACE-ESD | Number of new PhD and Msc students enrolled. | 32 PhD students and 45 Msc students enrolled |  | 7 new PhD students and 60 new Msc students enrolled |  |  | 7 new PhD students and 60 new Msc students enrolled |  | 50% | 82 candidates admitted in MSc of whom 20 are regionals and 62 are nationals. The call for application in PhD under the sponsorship of UR-SIDA program is ongoing. | 0PhD and 72 Msc including 15 international students enrolled | 0.8 | Out of 121 admitted in MSc only 72 enrolled due to the limited sponsorship provided by the center (35) and HEC (47). Others were required to look for self-sponsorship thus preferred to do not register. For PhD under SIDA program, after the call, there was no candidate who showed the interest within the UR staff. Going forward, the call will be re-advertised targeting external Rwandans.
7 | African center of excellence in internet of things (ACE IoT) | New PhD students and Msc enrolled in ACE-IoT | Number of new PhD and Master students enrolled | 5 PhD students and 84 Msc students |  | 4 new PhD students and 30 Msc enrolled |  |  | 4 new PhD students and 30 Msc enrolled | 0 | 50% | The selection for both PhD and MSc applications is ongoing toward admission and enrollment in Q2. | 5 PhD students and 46 Msc students | 0.77 | Out of 67 admitted in MSc only 46 enrolled due to the limited sponsorship provided by the center and HEC. Others were required to look for self-sponsorship thus preferred to do not register.
8 | Priority skills for Growth (PSG) | 3 new programs in transport and logistics developed and accredited 3 programs in agro-processing updated and accredited | Number of new programmes in T&L developed and accredited | Draft programmes |  |  |  | 3 new programmes | 3 new programmes | 2 new programs developped | 80% | 2 new BSc curricula in transport and logistics engineering and T& management have been developped, approved by UR senate and submitted to HEC for accreditation. The 1st enrollment is expected in Q2. The industrial attachment of academic staff to deliver those programs have been conducted with potential local industries. The acquisition of laboratory equipment for this program is at the stage of tender advertisement. | 2 developed programs are accredited by HEC | 100% | The developed undergraduate programs are new and are to be implemented by the College of Science and Technology (CST) and College of business and Economics for T&L Engineering and T&L Management programs respectively. As the accreditation was issued after expiration of admission and enrolment period in UR, it is expected that the 1st intake will be in next academic year. the tender for lab equipment is published and opening of bids is planned on 27th February 2020.
|  |  | Number of programmes in agro-processioning updated and accredited |  |  |  |  | 3 new programmes | 3 new programmes | 4 programs updated | 80% | 4 existing programs Curricula (Agricultural Mechanization, Food Science and Technology, Horticulture, Crop Production) have been updated, approved by UR Senate and submitted to HEC for accreditation.The industrial attachment of academic staff to deliver those programs have been conducted with potential local industries. The acquisition of laboratory equipment for this program is at the stage of tender advertisement. | 4 updated programs are accredited by HEC | 100% | The updated undergraduate programs are the already existing programs implemented by the college of agriculture (CAVM). For it to be smoothly implemented, there still a need to establish modern laboratory: the tender is published and opening of bids is planned on 27th February.
9 | ICTP-EAIFR (East African Institute for Fundamental Research) | 8 new PhD students and 30 new Msc students enrolled | Number of new PhD and Msc students enrolled | 10 ongoing Msc students enrolled | 8 new PhD students enrolled | 30 new Msc students enrolled |  |  | 8 new PhD students and 30 new Msc students enrolled | 0 PhD enrolled, 16 new Msc candidates admitted | 50% | Received applications for PhD and are being analyzed jointhly with the ICTP-Triester (Italy) as well as securing schoolarships for candidates | 6 PhD students admitted and 10 MSc students enrolled | 50% | Among 105 applications, 16 were admitted in MSc of which 10 managed to enrol due to the limited sponsorship: ICTP sponsored 6 of them and HEC funded 4. For PhD program, among 37 application, 6 were admitted now looking for funding opportunity to be able to enrol. The internationality character of this centre and its scientific level which targets high level research in physics make the program high demanding in terms of finance for selected students which limits the number of enrolment.
10 | Nyagatare Veterinary Laboratory | Nyagatare Veterinary Complex constructed. | % completion of construction works | 11% | 20% | 30% | 40% | 50% | 50% | 11% | 11% | This project is dormant because it does not have budget for this FY. Thus, both tender and activities could not be performed. | 11% | 0% | This project is dormant because it does not have budget for this FY. Thus, both tender and activities could not be performed.
ARES
FOJO
SIDA

## Finance
Project Information |  |  | Disbursement | [5 empty] | Spending | [5 empty] | Comment
SN | Project name | Funder | Previous | Q1 | Q2 | Q3 | Q4 | Annual | Previous | Q1 | Q2 | Q3 | Q4 | Annual | Previous | Q1 | Q2 | Q3 | Q4 | Annual
1 | Construction of the Centre for Biomedical Engineering and e-Health (CEBE) complex | AFRICAN DEVELOPMENT FUND FOR ADB | 1783707.87 |  | 1327155.98 |  |  | 1327155.98 | 958449.42 | 170483.36 | 1444129.98 | 2573062.76 |  | 4187676.1
|  | CENTRAL TREASURY | 22039356 |  |  |  |  | 0 | 22039356 | 0 |  |  |  | 0
2 | UR Infrastructure Development | IMPORT EXPORT BANK OF KOREA | 10416889.2806 | 1774927.32 | 2521131.37 |  |  | 4296058.69 | 10416889.2806 | 1774927.32 | 2521131.37 |  |  | 4296058.69 | The 1st invoice of construction works amounting $2,345,164 is pending for payment |  | the spending including advance paid against contracted amount is at 34% which quite good compared to the physical progress. However, this rate does not take into consideration into account the contigence funds which still unallocated. | Add consultant invoice
|  | CENTRAL TREASURY | 0 | 0 | 781084906 |  |  | 781084906 | 0 |  | 781084906 |  |  | 781084906 | The taxes for paid invoices from both consultant and contractor (estimated at $1.5M) are being calculated for its payoff in Q2 |  | The tax paid was to cover the paid invoices of consultant since the beginning.
3 | Regional Center Of Excellence For Vaccines, Immunization and Health Supply Chain Management (RCE-HSCM) | KfW | 1656571.17 | 0 | 552255 |  |  | 552255 | 1286444.5274 | 279706.7563 | 241039.8809 |  |  | 520746.6372 |  |  | the stated expenditure excludes the payment made to the consultant (HERA)
|  | CENTRAL TREASURY |  | 3711073 | 1740351 |  |  | 5451424 |  | 3711073 | 1740351 |  |  | 5451424 |  |  | The paid amount is to cover taxes on paid invoices to the consultant
4 | Africa Center of Excellence for Innovative Teaching and Learning Mathematics and Science (ACE ITLMS) | WORLD BANK/INTERNATIONAL DEVELOPMENT ASSOCIATION (IDA) | 1611773.6 | 167589.15 | 0 |  |  | 167589.15 | 789951.95 | 153069 | 194553.96 |  |  | 347622.96
5 | African Center of Excellence in Data Sciences (ACE DS) | WORLD BANK/INTERNATIONAL DEVELOPMENT ASSOCIATION (IDA) | 1539751.77 | 535221 | 0 |  |  | 535221 | 872157.5166 | 115222 | 169914.88 |  |  | 285136.88
6 | African center of excellence in energy for sustainable development (ACE ESD) | WORLD BANK/INTERNATIONAL DEVELOPMENT ASSOCIATION (IDA) | 1968361.51 | 506289 | 0 |  |  | 506289 | 1031405.1 | 152253.6 | 516476.97 |  |  | 668730.57
7 | African center of excellence in internet of things (ACE IoT) | WORLD BANK/INTERNATIONAL DEVELOPMENT ASSOCIATION (IDA) | 1787947.51 | 643779.31 | 0 |  |  | 643779.31 | 717239.93 | 91958.34 | 116410 |  |  | 208368.34
8 | Priority skills for Growth (PSG) | WORLD BANK/INTERNATIONAL DEVELOPMENT ASSOCIATION (IDA) | 272226880 | 0 |  |  |  | 0 | 89453760 | 19341630 | 0 |  |  | 19341630 | The spending of this project is very low compared to the budget due to the fact that the tendering for laboratory equipment is not yet concluded. The only spent money was on curriculum development and industrial attachment of academic staff. |  | The spending of this project is very low compared to the budget due to the fact that the tendering for laboratory equipment is not yet concluded.
9 | ICTP-EAIFR (East African Institute for Fundamental Research) | CENTRAL TREASURY | 627149246 | 0 |  |  |  | 0 | 374594184 | 74867644 | 139537685 |  |  | 214405329
10 | Nyagatare Veterinary Laboratory | CENTRAL TREASURY | 980603567 | 0 |  |  |  | 0 | 980603567 | 0 | 0 |  |  | 0
374594184
Note on K13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: subject to change upon correction of financial report

## performance
S/N | Project name | Estimated Overall Physical Performance (%)
|  | 2019-06-01 | 2019-09-01 | 2019-12-01
1 | East Africa Centre of Excellence for Biomedical engineering and E-health (CEBE) | 10% | 12% | 18%
2 | UR Infrastructure Development Project (IDP) | 8% | 15% | 30.5%
3 | Regional Center Of Excellence For Vaccines, Immunization and Health Supply Chain Management (RCE-HSCM) | 30% | 36% | 40%
4 | Africa Center of Excellence for Innovative Teaching and Learning Mathematics and Science (ACE ITLMS) | 60% | 67% | 70%
5 | African Center of Excellence in Data Sciences (ACE DS) | 64.82% | 67% | 70%
6 | African center of excellence in energy for sustainable development (ACE ESD) | 64.14% | 66% | 70%
7 | African center of excellence in internet of things (ACE IoT) | 60.42% | 65% | 70%
8 | Priority skills for Growth (PSG) | 10% | 50% | 80%
9 | East African Institute for Fundamental Research (ICTP/EAIFR) | 15% | 20% | 22%
10 | Nyagatare Veterinary Complex | 11.3% | 11.3% | 11%

## IDP
| Project cost | 56257680117
| Contractor total cost | 39589914.26 |  | 56257680117
| Consultant total cost | 3673611.0484
2015-08-12 | Advance for consultancy service | 711710.9939
2016-09-16 | Invoice #1 consultancy service | 533783.2431 |  | 56257680117
2017-04-07 | Invoice #2 consultancy service | 533783.2243
2018-12-20 | Advance for contractor (20%) | 7925900.8348 |  | 60962000 | 9714000
2018-12-21 | Invoice #3 consultancy service | 355855.4923 |  | 51248000
2019-04-29 | Invoice #4 consultancy service (Q1 construction) | 355855.4923 |  | 922.8319
| Invoice #1 contractor (12%) | 1641614.32
| Invoice #2 contractor (12%) | 1698305.96
| Invoice #3 contractor (6%) | 822825.41 |  | 1122882300
| Invoice for capacity building (upon invitation: 30%) | 133313
12118770873.5496
| Total | 14712947.9706 | 34.01%
13241653173.5496